## RFI
[7 empty] | PROJECT |  |  |  | VIOLA ENERGY CENTER
[7 empty] | ITEM |  |  |  | EVAPCO DRY COOLING, INC
[7 empty] | CLIENT |  |  |  | STEEL STRUCTURE (200POR241141)
REQUEST FOR INSPECTION (RFI)
| RFI No. | [10 empty] | Rev. No. |  |  |  | RFI Submission Date
| 200POR241141-VIOLA-RFI-A033 | [10 empty] | 0 |  |  |  | 2026-05-26
Discipline
|  | Mock-Up |  |  |  | Raw Material |  | Welding |  | NDT |  | Dimension | Pre-assembly | Coating | Packing & Final |  | x | Other
Work To Be Inspected (Description As Per ITP )
| Item no: |  |  |  | 3.2
| ITP Doc. Reference no. | [10 empty] | Fabrication Yard |  |  |  | Date Of Inspection
| DDC-QAQC-VIO20025-ITP-001 | [10 empty] | DDC AH |  |  |  | 2026-05-26
| Member Type | [10 empty] | Attachment(s) |  |  |  | Time Of Inspection
| BTG | [10 empty] | List of member |  |  |  | 15:00
EVALUATION BY SUPERVISION CONSULTANT/ CLIENT
Accept
Reject
Accept with Comments
Comments
DDC QC INSPECTOR | [8 empty] | CLIENT (EVAPCO) |  |  |  |  | OWNER
Name: |  |  |  | NGUYỄN VĂN TRÌNH |  |  |  |  | Name: |  |  |  |  | Name:
TRÌNH
Signature: | [8 empty] | Signature: |  |  |  |  | Signature:
Date: |  |  | 2026-05-26 | [5 empty] | Date: |  |  |  |  | Date:

## MEMBER LIST
|  | PROJECT | VIOLA ENERGY CENTER
|  | ITEM | EVAPCO DRY COOLING, INC
|  | CLIENT | STEEL STRUCTURE (200POR241141)
LIST OF MEMBER
RFI No.
| 200POR241141-VIOLA-RFI-A033 | [16 empty] | 2023-12-14
No. | Item No. | Drawing No. | Rev | Q.ty | Weight (kg) | Unit | Inspection Stage | LOCATION | DDC INS | Verified By | ACC/ REJ | Remark | Milestone
1 | 02BTG3005-001 | BTG3005 | 2 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2 | 5 | 1 | Dimension+Visual+NDT | 3.10, 3.3, 3.6, 3.7
2 | 02BTG3005-002 | BTG3005 | 2 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2 |  | 2 | Dimension+Visual | 3.10, 3.3
3 | 02BTG3039-001 | BTG3039 | 3 | 1 | 2364.38 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2 |  | 3 | Final Dimension | 3.1
4 | 02BTG3059-001 | BTG3059 | 0 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2 |  | 4 | Trial Assembly | 3.11
5 | 02BTG3059-002 | BTG3059 | 0 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2 |  | 5 | Fit-up | 3.2
6 | 03BTG3005-001 | BTG3005 | 2 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
7 | 03BTG3005-002 | BTG3005 | 2 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
8 | 04BTG3005-001 | BTG3005 | 2 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
9 | 04BTG3005-002 | BTG3005 | 2 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
10 | 04BTG3010-002 | BTG3010 | 2 | 1 | 303.06 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
11 | 04BTG3059-001 | BTG3059 | 0 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
12 | 05BTG3005-001 | BTG3005 | 2 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
13 | 05BTG3005-002 | BTG3005 | 2 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
14 | 05BTG3010-001 | BTG3010 | 2 | 1 | 303.13 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
15 | 05BTG3010-002 | BTG3010 | 2 | 1 | 303.06 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
16 | 06BTG3005-001 | BTG3005 | 2 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
17 | 06BTG3005-002 | BTG3005 | 2 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
18 | 06BTG3010-001 | BTG3010 | 2 | 1 | 303.13 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
19 | 06BTG3010-002 | BTG3010 | 2 | 1 | 303.06 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
20 | 06BTG3059-001 | BTG3059 | 0 | 1 | 257.98 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
21 | 06BTG3059-002 | BTG3059 | 0 | 1 | 258.05 | PC | Fit-Up | AH9 | TRÌNH |  |  |  | Milestone 2
21
DDC QC INSPECTOR |  |  |  | CLIENT (EVAPCO) |  |  |  |  | OWNER
Name: | NGUYỄN VĂN TRÌNH |  |  | Name: |  |  |  |  | Name:
Signature: |  |  |  | Signature: |  |  |  |  | Signature:
Date: | 2026-05-26 |  |  | Date: |  |  |  |  | Date: